CSD 460 Capstone in Software Development

Module 1 – Assignment 2
Moffat Bay Marina Technical Design Document
Section 1.5: Work Estimations (To-Do List)

| Student | Group | Project |
| --- | --- | --- |
| Aftabur Rahman | Green | Moffat Bay Marina |

# 1.5 Work Estimations (To-Do List)

Purpose

This section translates the team's nine existing user stories (UST-01 through UST-09) into prioritized development work, estimated hours, and actionable To-Do tasks for the Moffat Bay Tasks Kanban board. The estimates are proposed planning estimates and should be reviewed by Group Green using Planning Poker.

## Prioritized User Stories and Total Estimated Hours

| Priority | User Story | Description | Total Hours |
| --- | --- | --- | --- |
| 1 | UST-03 | Easy sign-up including customer and boat information | 8 |
| 2 | UST-05 | Unavailable slip notification and waitlist process | 8 |
| 3 | UST-07 | Detailed reservation summary | 6 |
| 4 | UST-04 | Email verification and account security | 7 |
| 5 | UST-08 | Reservation lookup and history | 5 |
| 6 | UST-09 | Reservation cancellation | 4 |
| 7 | UST-01 | Public website access and contact information | 4 |
| 8 | UST-02 | Slip pricing information | 3 |
| 9 | UST-06 | Waitlist position/count | 3 |

| Total Proposed Effort | Hours |
| --- | --- |
| All nine user stories | 48 |

## Detailed Work Breakdown – Individual User Story Tables

Each user story is presented in its own separate table below. Each table has its own task breakdown and its own total estimated hours. This format makes the work easier to review and transfer to the Kanban board.

| User Story | Description |
| --- | --- |
| UST-01 – Public Website Access and Contact Information | The customer wants to view the full site without signing up and have a way to contact the marina. |

| To-Do Task | Story Hours |
| --- | --- |
| Create landing page structure and navigation | 1.0 |
| Create marina About Us/information content | 1.0 |
| Create Contact Us page and contact information | 1.0 |
| Test public pages without requiring login | 1.0 |
| TOTAL ESTIMATED HOURS | 4.0 |

| User Story | Description |
| --- | --- |
| UST-02 – Slip Pricing Information | The customer wants to understand the slip pricing formula and estimate cost before providing personal information. |

| To-Do Task | Story Hours |
| --- | --- |
| Add monthly slip pricing information | 0.75 |
| Document the $10 per foot plus $10 electric formula | 0.50 |
| Create/display example cost calculation | 0.75 |
| Test pricing examples and displayed information | 1.0 |
| TOTAL ESTIMATED HOURS | 3.0 |

| User Story | Description |
| --- | --- |
| UST-03 – Easy Sign-Up Including Boat Information | The customer wants an easy sign-up that includes personal and boat information in a single sign-up and reservation flow. |

| To-Do Task | Story Hours |
| --- | --- |
| Create registration/reservation form layout | 1.0 |
| Add customer information fields | 1.0 |
| Add boat name and boat length fields | 1.0 |
| Add email and password validation | 1.0 |
| Create/store customer account information | 1.5 |
| Create/store boat information | 1.0 |
| Connect registration information to reservation process | 1.0 |
| Test registration and boat-information workflow | 0.5 |
| TOTAL ESTIMATED HOURS | 8.0 |

| User Story | Description |
| --- | --- |
| UST-04 – Email Verification and Account Security | The customer wants an easy-to-follow email verification process and secure account information. |

| To-Do Task | Story Hours |
| --- | --- |
| Create login/authentication workflow | 1.0 |
| Implement email-format validation | 0.75 |
| Implement email verification workflow | 1.5 |
| Implement password security requirements | 1.0 |
| Implement secure password storage | 1.0 |
| Create session management | 1.0 |
| Test authentication and verification scenarios | 0.75 |
| TOTAL ESTIMATED HOURS | 7.0 |

| User Story | Description |
| --- | --- |
| UST-05 – Slip Availability and Waitlist | When the required slip size is unavailable, the customer should be informed and given a clear path to join the waitlist. |

| To-Do Task | Story Hours |
| --- | --- |
| Determine required slip size from boat length | 1.0 |
| Create/check slip availability logic | 1.5 |
| Connect available slips to reservation process | 1.0 |
| Display unavailable-slip notification | 0.5 |
| Create waitlist option | 1.0 |
| Store waitlist request | 1.0 |
| Cancel reservation attempt when no slip is available | 0.5 |
| Test available, unavailable, and waitlist scenarios | 1.5 |
| TOTAL ESTIMATED HOURS | 8.0 |

| User Story | Description |
| --- | --- |
| UST-06 – Waitlist Position/Count | The customer wants to know how many people are ahead of them before deciding whether to join the waitlist. |

| To-Do Task | Story Hours |
| --- | --- |
| Retrieve current waitlist count for slip category | 1.0 |
| Calculate/display number of customers ahead | 1.0 |
| Display waitlist position before commitment | 0.5 |
| Test waitlist count and position scenarios | 0.5 |
| TOTAL ESTIMATED HOURS | 3.0 |

| User Story | Description |
| --- | --- |
| UST-07 – Detailed Reservation Summary | The customer needs a reservation summary containing boat information, slip size, slip number, check-in date, and total cost. |

| To-Do Task | Story Hours |
| --- | --- |
| Create reservation summary page | 1.0 |
| Display boat information | 0.5 |
| Display assigned slip size | 0.5 |
| Display slip number | 0.5 |
| Display check-in date | 0.5 |
| Calculate/display total cost | 1.0 |
| Add confirm reservation functionality | 0.75 |
| Add cancel functionality | 0.75 |
| Test reservation summary | 0.5 |
| TOTAL ESTIMATED HOURS | 6.0 |

| User Story | Description |
| --- | --- |
| UST-08 – Reservation Lookup and History | A returning customer wants to see reservation IDs and information about previous reservations, including dates and slips used. |

| To-Do Task | Story Hours |
| --- | --- |
| Create reservation lookup page/form | 1.0 |
| Implement reservation ID search | 0.75 |
| Implement email-based search | 0.75 |
| Retrieve reservation history from database | 1.0 |
| Display reservation dates and slip information | 1.0 |
| Test lookup and history results | 0.5 |
| TOTAL ESTIMATED HOURS | 5.0 |

| User Story | Description |
| --- | --- |
| UST-09 – Reservation Cancellation | A returning customer wants to cancel a reservation from the summary page and return to the reservation page without negatively affecting the reservation history. |

| To-Do Task | Story Hours |
| --- | --- |
| Add cancellation control to reservation summary | 0.5 |
| Implement reservation cancellation logic | 1.0 |
| Update reservation status/availability | 1.0 |
| Return customer to reservation page | 0.5 |
| Verify reservation history remains accurate | 0.5 |
| Test cancellation scenarios | 0.5 |
| TOTAL ESTIMATED HOURS | 4.0 |

## Kanban To-Do List

The following are the actionable tasks to provide to the team leader/delegate for the Moffat Bay Tasks Kanban board.

| User Story | Kanban Task | Hours |
| --- | --- | --- |
| UST-01 – Public Website Access and Contact Information | Create landing page structure and navigation | 1.0 |
| UST-01 – Public Website Access and Contact Information | Create marina About Us/information content | 1.0 |
| UST-01 – Public Website Access and Contact Information | Create Contact Us page and contact information | 1.0 |
| UST-01 – Public Website Access and Contact Information | Test public pages without requiring login | 1.0 |

| User Story Total | Total Hours |
| --- | --- |
| UST-01 – Public Website Access and Contact Information | 4.0 |

| User Story | Kanban Task | Hours |
| --- | --- | --- |
| UST-02 – Slip Pricing Information | Add monthly slip pricing information | 0.75 |
| UST-02 – Slip Pricing Information | Document the $10 per foot plus $10 electric formula | 0.50 |
| UST-02 – Slip Pricing Information | Create/display example cost calculation | 0.75 |
| UST-02 – Slip Pricing Information | Test pricing examples and displayed information | 1.0 |

| User Story Total | Total Hours |
| --- | --- |
| UST-02 – Slip Pricing Information | 3.0 |

| User Story | Kanban Task | Hours |
| --- | --- | --- |
| UST-03 – Easy Sign-Up Including Boat Information | Create registration/reservation form layout | 1.0 |
| UST-03 – Easy Sign-Up Including Boat Information | Add customer information fields | 1.0 |
| UST-03 – Easy Sign-Up Including Boat Information | Add boat name and boat length fields | 1.0 |
| UST-03 – Easy Sign-Up Including Boat Information | Add email and password validation | 1.0 |
| UST-03 – Easy Sign-Up Including Boat Information | Create/store customer account information | 1.5 |
| UST-03 – Easy Sign-Up Including Boat Information | Create/store boat information | 1.0 |
| UST-03 – Easy Sign-Up Including Boat Information | Connect registration information to reservation process | 1.0 |
| UST-03 – Easy Sign-Up Including Boat Information | Test registration and boat-information workflow | 0.5 |

| User Story Total | Total Hours |
| --- | --- |
| UST-03 – Easy Sign-Up Including Boat Information | 8.0 |

| User Story | Kanban Task | Hours |
| --- | --- | --- |
| UST-04 – Email Verification and Account Security | Create login/authentication workflow | 1.0 |
| UST-04 – Email Verification and Account Security | Implement email-format validation | 0.75 |
| UST-04 – Email Verification and Account Security | Implement email verification workflow | 1.5 |
| UST-04 – Email Verification and Account Security | Implement password security requirements | 1.0 |
| UST-04 – Email Verification and Account Security | Implement secure password storage | 1.0 |
| UST-04 – Email Verification and Account Security | Create session management | 1.0 |
| UST-04 – Email Verification and Account Security | Test authentication and verification scenarios | 0.75 |

| User Story Total | Total Hours |
| --- | --- |
| UST-04 – Email Verification and Account Security | 7.0 |

| User Story | Kanban Task | Hours |
| --- | --- | --- |
| UST-05 – Slip Availability and Waitlist | Determine required slip size from boat length | 1.0 |
| UST-05 – Slip Availability and Waitlist | Create/check slip availability logic | 1.5 |
| UST-05 – Slip Availability and Waitlist | Connect available slips to reservation process | 1.0 |
| UST-05 – Slip Availability and Waitlist | Display unavailable-slip notification | 0.5 |
| UST-05 – Slip Availability and Waitlist | Create waitlist option | 1.0 |
| UST-05 – Slip Availability and Waitlist | Store waitlist request | 1.0 |
| UST-05 – Slip Availability and Waitlist | Cancel reservation attempt when no slip is available | 0.5 |
| UST-05 – Slip Availability and Waitlist | Test available, unavailable, and waitlist scenarios | 1.5 |

| User Story Total | Total Hours |
| --- | --- |
| UST-05 – Slip Availability and Waitlist | 8.0 |

| User Story | Kanban Task | Hours |
| --- | --- | --- |
| UST-06 – Waitlist Position/Count | Retrieve current waitlist count for slip category | 1.0 |
| UST-06 – Waitlist Position/Count | Calculate/display number of customers ahead | 1.0 |
| UST-06 – Waitlist Position/Count | Display waitlist position before commitment | 0.5 |
| UST-06 – Waitlist Position/Count | Test waitlist count and position scenarios | 0.5 |

| User Story Total | Total Hours |
| --- | --- |
| UST-06 – Waitlist Position/Count | 3.0 |

| User Story | Kanban Task | Hours |
| --- | --- | --- |
| UST-07 – Detailed Reservation Summary | Create reservation summary page | 1.0 |
| UST-07 – Detailed Reservation Summary | Display boat information | 0.5 |
| UST-07 – Detailed Reservation Summary | Display assigned slip size | 0.5 |
| UST-07 – Detailed Reservation Summary | Display slip number | 0.5 |
| UST-07 – Detailed Reservation Summary | Display check-in date | 0.5 |
| UST-07 – Detailed Reservation Summary | Calculate/display total cost | 1.0 |
| UST-07 – Detailed Reservation Summary | Add confirm reservation functionality | 0.75 |
| UST-07 – Detailed Reservation Summary | Add cancel functionality | 0.75 |
| UST-07 – Detailed Reservation Summary | Test reservation summary | 0.5 |

| User Story Total | Total Hours |
| --- | --- |
| UST-07 – Detailed Reservation Summary | 6.0 |

| User Story | Kanban Task | Hours |
| --- | --- | --- |
| UST-08 – Reservation Lookup and History | Create reservation lookup page/form | 1.0 |
| UST-08 – Reservation Lookup and History | Implement reservation ID search | 0.75 |
| UST-08 – Reservation Lookup and History | Implement email-based search | 0.75 |
| UST-08 – Reservation Lookup and History | Retrieve reservation history from database | 1.0 |
| UST-08 – Reservation Lookup and History | Display reservation dates and slip information | 1.0 |
| UST-08 – Reservation Lookup and History | Test lookup and history results | 0.5 |

| User Story Total | Total Hours |
| --- | --- |
| UST-08 – Reservation Lookup and History | 5.0 |

| User Story | Kanban Task | Hours |
| --- | --- | --- |
| UST-09 – Reservation Cancellation | Add cancellation control to reservation summary | 0.5 |
| UST-09 – Reservation Cancellation | Implement reservation cancellation logic | 1.0 |
| UST-09 – Reservation Cancellation | Update reservation status/availability | 1.0 |
| UST-09 – Reservation Cancellation | Return customer to reservation page | 0.5 |
| UST-09 – Reservation Cancellation | Verify reservation history remains accurate | 0.5 |
| UST-09 – Reservation Cancellation | Test cancellation scenarios | 0.5 |

| User Story Total | Total Hours |
| --- | --- |
| UST-09 – Reservation Cancellation | 4.0 |

## Planning and Estimation Note

| Item | Statement |
| --- | --- |
| Estimate status | The hour values are proposed estimates based on the team's existing UST-01 through UST-09. They are not instructor-provided values. |
| Team review | Group Green should review and approve or adjust the estimates using Planning Poker before final submission. |
| Kanban | The approved tasks should be added to the Moffat Bay Tasks Kanban board by the team leader or delegate. |

Prepared for CSD 460 Module 1 – Assignment 2 | Group Green